**Darnhall primary school P.E. Action Plan September 2020 – 2021**

**To raise standards of Health and Fitness and Physical Education across the school.**

**MAY CHANGE DUE TO COVID-19 SOCIAL DISTANCE REGIME**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Success Criteria** | **Action Planned** | **Timescale**  **Start** | **Timescale**  **End** | **Lead Person(s)** | **Resources** | **Monitoring Arrangements** | **Evidence and Evaluation** | **Progress**  **To date:** |
| Maintain the provision of lunchtime activities and increase the profile of Lunchtime Sports Leaders. | Playleaders who take part in the training with Tom to lead competitive games at dinner time.  Audit resources and use PE funding to improve provision  Maintain Golden Mile program | Sept 20 | Sept 21 | Mr Dunning  (P.E. lead)  Mr. Baxendale  (Yr. 6 Teacher) | PE funding  Teaching Assistants | Observation and meetings with staff. (Staff meetings).  Monthly meetings with sports council to hear their feedback. |  |  |
| Maintain well-being sessions to the PE curriculum to promote healthy lifestyles. (My Personal Best programme) | Through PE curriculum and promoted through healthy eating initiatives and adults working across school.  PSHE lessons and wellbeing week. | Sept 20 | July 21 | All staff / Mr. Dunning | PE funding  Teaching Assistants  Outside agencies | Social media  Evidence on Ipads  Evidence in Class portfolio | To see improvements in levels of fitness and obesity across the school. |  |
| Introduce virtual P.E. sessions considering the Covid-19 global pandemic. | Virtual P.E. sessions and daily challenges to be set so children can access activities at home. | Sept 20 | July 21 | Mr. Dunning  Teaching staff | Social media platforms  Vale Royal SSP | Mr. Dunning to closely monitor children engaging in virtual activities | TopYa! P.E. app |  |
| To analyse assessment data at half termly intervals and identify children requiring additional support in different aspects of P.E. | Ability groupings in PE specific support. (Teaching assistants to work with this group with the Teacher closely observing).  Teaching staff to report to Mr. Dunning and communicate which children who are not meeting or exceeding expectation | Sept 20 | July 21 | Mr. Dunning | Vale Royal Data tracker on staff share | Meetings half termly  P.E. Staff meetings | Vale Royal data tracker |  |
| Balanced curriculum offered of varied sports with a competitive element in curriculum time. | All PE sessions to have competitive element at some stage of session  Curriculum Appropriately resourced | Sept 20 | July 21 | Class Teaching staff  Mr. Dunning | PE Funding | Observations and learning walks | Observations and learning walks feedback |  |
| Identify pupils with specific skills and signpost these to organisations beyond school. | Varied opportunities offered for ability ranges.  Communication with school and local sports teams | Sept 20 | July 21 | Class Teaching staff  Mr. Dunning | PE Funding | Regular discussion with teaching staff and Mr. Dunning.  Mr. Dunning to communicate with parents. | Vale Royal competition tracker |  |
| Train junior sports leaders and sports council to offer additional support in delivering and supporting P.E.  (Sports council) | Sports council members to help deliver some P.E. lessons alongside class teacher. | Sept 20 | July 21 | Mr. Dunning | PE Funding  Play Leaders training | Mr. Dunning to lead sports leader provision and opportunities and record involvement. |  |  |
| Questionnaire children about extra-curriculum clubs they would like. Use this to implement specific activities. | Complete questionnaire from F2 to Year 6 to gauge appeal of different. | Oct 20 | Nov 21 | Mr. Dunning |  | Meeting to analyse data. |  |  |
| All year groups to be given varied termly competitive inter school competition opportunities throughout the year | Cluster meetings to plan competitions across Winsford.  Vale Royal sport calendar to be used by Mr. Dunning. | Sept 20 | July 21 | Mr. Dunning and Mr. Baxendale. | Cluster budget available | Cluster meetings half termly with Chris Story. |  |  |
| Whole school (F2 to Year 6) to compete in intra – school activities before end of academic year. | Golden Mile programme to be re-introduced every day.  Sports day  Sporting friendlies with other close Winsford school’s | Sept 20 | July 21 | Mr. Dunning  Mr. Baxendale |  |  |  |  |
| 100% of KS2 to be offered opportunity to compete in inter school activities. | Cluster and Vale Royal events attended regularly | Sept 20 | July 21 | Mr. Dunning |  | Termly updates on numbers taking part updated |  |  |